KYNORML Executive Director Operations Handbook

Prepared for leadership transition — Deputy Director to Executive Director · June 2026

Why This Document Exists

This is a complete transition document — built to hand every recurring operational responsibility of the Executive Director role from the outgoing Deputy Director to whoever holds or inherits the ED position. Nothing about how KYNORML actually runs should live only in one person's head.

The work runs on five different rhythms: daily, bi-weekly, monthly, seasonal (KYCannaCon production, September–March), and annual. This document covers all five. If you're stepping into this role, this is the full picture of what it takes to keep the chapter running.

The source playbooks (Financial Box, Governance Box, Chapter Health Dashboard, Marketing Master Calendar, Track 1 - Email Campaign System, Track 2 - Social Media System, Track 4 - PR Response System, KYCannaCon Conference Playbook) stay current and authoritative — this document is the assembled, KYNORML-specific view of when and in what order to run them.

The Entity Map — Who's Who

A new ED inherits not just KYNORML but a small web of related entities. Money, services, and compliance obligations move between them — misunderstanding the map causes real problems.

| Entity | What It Is | Relationship to KYNORML |
| --- | --- | --- |
| KYNORML, INC | The 501(c)(4) social welfare organization — the chapter itself. Advocacy, lobbying, KYCannaCon, membership, directory. Donations are not tax-deductible. | This is the organization you're running. |
| Common Good Network (CGN) | A 501(c)(3) educational nonprofit — the education arm. Runs Google Ad Grants ($10,000/month in free advertising), cannabis wellness education, and anything requiring tax-deductible donations or grant eligibility. | Separate legal entity, same mission family. KYNORML and CGN must keep finances, messaging, and activities legally distinct — this is the single most important compliance boundary to understand on day one. Confirm with legal/accounting how the two currently divide work before assuming anything is shared. |
| Verdant Management Partners (VMP) | Lauren Bratcher's professional services and event-management company. Produces KYCannaCon, consults for other NORML chapters, and is a vendor/contractor to KYNORML — not part of the org chart. | Any work VMP does for KYNORML should be under a written agreement with clear payment terms. See the Vendor Contract Template in Financial Box. |
| Verdant Ventures LLC | Lauren's personal vendor entity. Bills VMP for Lauren's work directly. | No direct relationship to KYNORML — two layers removed. If you see a direct KYNORML-to-Verdant Ventures transaction, that's a red flag worth raising with the board. |
| National NORML | The parent organization. Provides the chapter charter, free press/social content, chapter directory network, and national advocacy resources. | KYNORML operates as a state chapter — not a subsidiary. Distribution, branding, and content flow from this relationship. Chapter has reporting obligations and branding guidelines to follow. |

The compliance line that matters most: KYNORML (advocacy) and CGN (education) must stay legally distinct. VMP and Verdant Ventures are Lauren's outside businesses — treat them with the same written-agreement, arm's-length standards you'd apply to any vendor.

Full Scope of the Role — At a Glance

Every recurring task the ED is responsible for, organized by frequency. Nothing in this list is optional — if something stops happening, the chapter starts degrading.

| Frequency | Area | Task |
| --- | --- | --- |
| Daily | Advocacy | Check Google Alerts digest for Kentucky cannabis news |
| Daily | Social | 5 min Threads engagement — reply to cannabis policy conversations |
| Daily | Operations | Respond to urgent inbox items (media, sponsors, board, directory inquiries) |
| Daily | Instagram | Post one Story — casual, behind-the-scenes, phone quality is fine |
| Every 2 weeks | Social media | Run the 2.5-hour batch session — creates 21 scheduled posts across FB/IG/Threads |
| Every 2 weeks | Email | Check that the next campaign is loaded, tested, and queued |
| Every 2 weeks | Revenue | Directory outreach batch, membership follow-ups, sponsor pipeline touches |
| Monthly | Finance | Pull P&L snapshot and reserve check |
| Monthly | Analytics | Pull full KPI dashboard (list, social, revenue, membership, advocacy) |
| Monthly | Fundraising | Run stewardship cadence — directory, membership, sponsors, donors |
| Monthly | Team | Review contractor invoices, check in with Shealonda/Maurice/James |
| Monthly | List | Email list hygiene — bounce cleanup, segment review |
| Monthly | Directory | Audit listings — expired, updated, new businesses to add |
| Monthly | Website | Spot-check key pages, links, and membership/donation flows |
| Monthly | National NORML | Check-in — chapter obligations, content to repurpose, national updates |
| Monthly (if meeting) | Board | Prep board packet; run meeting; file minutes |
| Monthly | Compliance | Check compliance calendar — anything due in next 60 days? |
| Monthly | Marketing | Sync with Marketing Master Calendar — confirm email, social, press on track |
| Seasonal (Sept–March) | KYCannaCon | Full conference production cycle — venue, speakers, sponsors, tickets, AV, day-of |
| Annual | Finance | Board approves operating budget (start of fiscal year) |
| Annual | Compliance | Form 990 filed by May 15 |
| Annual | Compliance | State annual report filed by incorporation anniversary |
| Annual | Compliance | State charitable solicitation registration renewed |
| Annual | Governance | Board conflict-of-interest policy signed by all members |
| Annual | Governance | Board elections / term renewals |
| Annual | Strategy | Annual chapter review — scorecard, wins/losses, one priority for next year |
| Annual | Revenue | Merch planning — new products for the year |
| Annual | Google Ads | Review Google Ad Grants performance via CGN — confirm $10K/month is being used |

Systems & Access Map

Every platform KYNORML runs on. Before transition is final, the incoming ED should be added as admin/owner on every row — not just a user.

| System | What It's For | Access Level Needed | Notes |
| --- | --- | --- | --- |
| Wave or QuickBooks | Bookkeeping — P&L, invoicing, expense tracking | Full admin (or shared with treasurer) | Wave is free; upgrade to QuickBooks once revenue exceeds $50K/year |
| Zeffy | Memberships ($25/mo, $250/yr), donations, event ticketing — 0% platform fee | Full admin | Confirm 501(c)(4) verification is complete on the platform |
| Action Network | The 8,000-person email list, advocacy alerts, segmentation, campaign scheduling | Full admin | Single largest audience asset — losing access is a major operational gap |
| Monday.com | Operations board, sponsor pipeline, conference production tracking (~$10–15/user/month) | Full admin / billing owner | Confirm current seat count and who pays |
| Buffer or Meta Business Suite | Social media scheduling — Facebook, Instagram, Threads | Full admin | See Track 2 - Social Media System |
| Google Workspace | Email, shared drives, calendar — runs under CGN | Admin or delegated admin | Confirm whether KYNORML has its own Workspace or operates within CGN's |
| Google Ad Grants | $10,000/month in free Google advertising — runs under CGN | Awareness + coordination | Currently idle — confirm status and whether it's being actively managed |
| Canva | Social graphics, sponsorship one-pager, event materials | Brand kit access | See KYCannaCon Sponsorship One-Pager |
| Bank account(s) | Operating account + reserve account (separate) | Authorized signatory | Requires dual signature on transactions over $500–1,000. Bank name, account structure, and current signatories are not documented in the vault — get this in writing during transition. |
| Social media accounts | Facebook, Instagram, Threads | Full owner on all three | Transfer ownership, not just login sharing |
| Website / CMS | Public site, directory, membership and donation links | Full admin | Confirm hosting provider, domain registrar, CMS login ownership |

Team — Who Does What

Three team members are named in vault records: Shealonda, Maurice, and James. Their specific roles are not documented here — closing this gap is one of the highest-value things the outgoing Deputy Director can do before leaving. A team that exists only as first names cannot be led by someone new.

Document for each person before transition:

☐  Full name and role/title

☐  What they own, day to day

☐  How to reach them and expected sync frequency

☐  Staff, contractor, or volunteer — and what that means for payroll/1099 obligations

☐  Any in-progress projects or standing commitments

Daily Work — Under 30 Minutes Total

These happen every working day. They're fast, but skipping them for a week shows up in the chapter's responsiveness and relevance.

Advocacy news monitoring (10 min)

Check the Google Alerts daily digest. Alerts are set for: Kentucky cannabis, Kentucky marijuana, NORML Kentucky, Kentucky medical cannabis, Kentucky cannabis legislation, Kentucky cannabis dispensary. Ask one question: does this news directly affect Kentucky cannabis patients? If yes, use the decision framework in Track 4 - PR Response System to decide whether to post, send an alert, or issue a press release. The response window is 24–48 hours — not a week.

Threads engagement (5 min)

Spend 5 minutes replying to relevant conversations in the cannabis policy space — other NORML chapters, advocates, legislators, journalists covering cannabis. Threads rewards participation, not just broadcasting. This is the fastest way to build relationships with the people who cover or influence the issue.

Instagram Story (5 min)

Post something once a day — a photo, a quick thought, a behind-the-scenes moment, a repost of someone tagging KYNORML. Phone quality is fine. No caption needed. This is the lowest-lift, highest-connection feature on Instagram and it compounds over time.

Inbox triage (10 min)

Respond to anything time-sensitive: directory listing inquiries (reply within 24 hours or lose the conversion), sponsor questions, media inquiries, board questions. Non-urgent items get flagged for the bi-weekly revenue or board workflow.

Every 2 Weeks — The Batch Session

Do not create content outside this window. Block 2.5 hours. Everything social and email lives here — doing it in batches prevents the daily friction that kills consistency.

The social batch session (2.5 hours every 2 weeks)

See Track 2 - Social Media System for the full workflow. Summary:

- Pull 3–4 recent national NORML posts or articles relevant to Kentucky

- Check KY cannabis news and your own calendar for the next 2 weeks

- Draft 7 core content ideas using the pillar rotation (Patient Resources, Policy + News, Action, Education, Community)

- For each idea, write 3 versions: Facebook (full caption + link), Instagram (punchy caption + graphic note), Threads (1–2 sentences, conversational)

- Pull/create 5–7 graphics for Instagram

- Schedule everything in Buffer or Meta Business Suite

- Add 3–5 extra Threads-only posts (reactions, polls, quick thoughts) to fill in the gaps

Result: 21 scheduled posts from 7 ideas, plus daily Stories and reactive posts as news breaks.

Email campaign check (30 min every 2 weeks)

Confirm the next scheduled email send in Track 1 - Email Campaign System is loaded in Action Network, links tested, and scheduled. The campaigns in priority order: KYCannaCon early bird tickets → KYCannaCon sponsor push → directory listing offer → membership drive → matching gift campaign. Do not send a campaign until it's been tested in a preview send.

Revenue pipeline touches (30 min every 2 weeks)

- Directory: send outreach batch to next 15 businesses using Campaign 4 template. Log every contact (name, business, date, response, follow-up date) in Google Sheet.

- Membership: check Zeffy for new signups; flag anyone in the non-opener sequence.

- Sponsors: check anyone in active conversation — anything that's gone quiet for 7+ days gets one follow-up touch.

Monthly Work

Run these in order, once a month. Total time: roughly half a day spread across the month.

Financial Snapshot

Pull from Wave or QuickBooks at the end of every month. Takes 20 minutes once the books are current.

|  | This Month | Year to Date | Budget | Variance |
| --- | --- | --- | --- | --- |
| Total Income |  |  |  |  |
| Total Expenses |  |  |  |  |
| Net |  |  |  |  |
| Cash on Hand |  |  |  |  |

Flag anything more than 15% off budget. No surprises allowed for the board.

Reserve check: Target is 3 months of operating expenses in a separate savings account — roughly $6,000 based on ~$2,000/month operating costs. Note where the chapter stands every month. Confirm the actual current operating cost and reserve balance with the books during transition — $2,000 is a planning baseline, not a confirmed actual.

Revenue stream targets to measure against:

| Stream | Monthly Target | How It's Built |
| --- | --- | --- |
| Directory listings | ~$750/month | 10 listings × ~$75/month — Campaign 4 in Track 1 - Email Campaign System |
| Memberships | ~$750/month | 30 members × $25/month (or $250/year annual tier) — Zeffy Membership Setup Guide |
| KYCannaCon sponsorships | $8,500+ upfront (seasonal, Nov–Mar) | Presenting $8,500 / Session $3,000 / Networking Reception $2,500 / Community $1,000 |
| Recurring monthly floor | ~$1,500/month | Directory + membership combined — this number should grow month over month |

Full detail and annual budget template: Financial Box

Monthly KPI Pull

Pull these numbers the same day as the financial snapshot — 15 minutes.

Audience and list: email list size, open rate (target ≥25%), click rate (target ≥3%), social followers, website visitors, directory page views

Revenue by stream: membership, donations, directory listings, merch, events, grants — log against the targets above

Membership: active members, new members this month, lapsed members this month, net change

Advocacy activity: action alerts sent, legislative contacts made, testimonies submitted, press releases issued, media mentions, events/appearances

The fast read: if cash, list growth, membership, and revenue are all green — the chapter is healthy. Two or more going yellow at the same time is the trigger to dig in before the quarterly board review.

Full tracker and health indicators (green/yellow/red scale): Chapter Health Dashboard

Fundraising and Stewardship Cadence

The month-by-month rhythm of keeping money moving in. Built around what actually converts on an advocacy list — not cold donation asks.

| Week | Action | Detail |
| --- | --- | --- |
| Week 1 | Membership pipeline | New signups logged in Zeffy; lapsed members in renewal sequence; non-opener follow-up sent if due |
| Week 1 | Directory pipeline | Conversion confirmations logged; renewal reminders sent if upcoming; new outreach batch loaded for the bi-weekly session |
| Week 2 | Sponsor pipeline | Anyone in active conversation gets a check-in; anyone gone quiet for 10+ days gets one follow-up, then moves to "dormant" in the tracker |
| Week 3 | Donor cultivation | Off-season months only (see Marketing Master Calendar for which months this applies) — reserve broad donation asks for matching-gift moments or genuine urgency |
| Week 4 | Revenue scorecard | Update actuals in Revenue Action Dashboard — this feeds the board packet |

The one rule: every touch gets logged. Pipeline that isn't logged gets forgotten.

The one annual donation moment that works: December — pair with the year-in-review press release and a matching gift offer if an anchor donor is secured. See Marketing Master Calendar → December row.

Team and Contractor Management

- Review any contractor invoices received this month — approve and process within 14 days per the reimbursement policy in Financial Box

- Touch base with Shealonda, Maurice, and James — anything blocked, behind, or needing a decision?

- If anyone is operating under a service agreement, confirm scope and timeline are still on track

- Any 1099 obligations for contractor payments over $600/year — flag for the treasurer before year-end

Email List Hygiene

The 8,000-person list degrades without maintenance. Once a month in Action Network:

- Review hard bounce rate — remove any hard bounces (bad addresses) from the active list

- Check unsubscribe rate on the most recent send — if it spikes above 1%, the send frequency or content mix needs a review

- Confirm the list segments are current (e.g., KYCannaCon attendees, members, high-engagement subset for donation asks)

- Note the current list size in the monthly KPI pull — the trend line matters more than the absolute number

Directory and Website Maintenance

The directory is a revenue engine and a community resource — it only serves both functions if it's accurate and current.

Directory (monthly):

- Review for expired or unresponsive listings — follow up on any that haven't renewed

- Add any new Kentucky cannabis businesses that have opened or come to your attention

- Confirm that featured/paid listings are displaying correctly

- Check for any outdated contact info, hours, or addresses

Website (monthly spot check):

- Confirm membership and donation links (Zeffy) are live and working — test them in a private browser

- Check the KYCannaCon event page — is the information current?

- Confirm contact info, social links, and navigation are correct

- Look for any broken links on high-traffic pages

National NORML Check-In

KYNORML operates under a chapter charter — there are obligations running in both directions.

Monthly:

- Check national NORML's website and social for new content, studies, or press to repurpose for Kentucky (free to use, credit the source)

- Confirm any chapter reporting requirements are current — ask if uncertain

- If VMP has an active engagement with national NORML (e.g., Chapter Summit production), confirm that project has its own separate workflow and isn't bleeding into KYNORML's operational time

Ongoing:

- Any national policy development affecting Kentucky patients should trigger the Track 4 - PR Response System reactive workflow within 24–48 hours

Board Meeting Preparation

Run every meeting that happens with this standard structure:

Standing agenda:

- Approval of previous minutes

- Financial report — monthly snapshot + variance flags

- Chapter health review — green/yellow/red on each indicator (full version quarterly per Chapter Health Dashboard)

- Old business — status of prior action items

- New business

- Action items with owners and due dates

- Next meeting date

Minutes: Use the Board Meeting Minutes Template in Governance Box. File every set on record — minimum one per year is required; every meeting is best practice.

Sound the alarm — off-cycle board conversation required for any of these:

- Cash drops below 1 month of operating expenses

- Email list declines 3 consecutive months

- 990 filing is overdue

- A board officer seat is vacant more than 60 days

- Revenue is more than 25% below budget at any quarter

- A key vendor or platform terminates the chapter's account

- Chapter is named in litigation

Compliance Calendar Check

Last week of every month: ask "is anything on this list due in the next 60 days?" If yes, it gets an owner and a date before the month closes.

| Requirement | When Due | Notes |
| --- | --- | --- |
| Form 990 filing | May 15 (calendar-year orgs) | 990-N under $50K, 990-EZ $50K–$200K, full 990 over $200K — start 60 days early |
| State annual report | Anniversary of incorporation date | Check Kentucky Secretary of State — confirm the actual date on the filing record |
| Charitable solicitation registration | Varies — usually annual renewal | Must be current before any active fundraising push |
| Conflict of interest policy | Annual — first board meeting of the year | All board members sign |
| Board meeting minutes on file | Minimum 1/year, every meeting preferred | Secretary's responsibility; ED confirms it's happening |

Monthly Marketing and Press Sync

- Confirm this month's row in Marketing Master Calendar — is the theme, social emphasis, email send, and press moment still accurate given what's actually happening?

- Is the month's scheduled email campaign loaded in Action Network and tested?

- If a planned press release is due this month, is a draft started at least a week ahead?

- If the calendar says "no press planned," don't force one — a thin release damages credibility more than silence

- Reactive PR runs on its own 24–48 hour clock on top of the planned calendar — it doesn't replace it

Media outlets to build relationships with (currently named as targets, not yet confirmed contacts): Louisville Courier-Journal, Kentucky Lantern (priority for embargoed exclusives), Bowling Green Daily News, WHAS11/WDRB local TV, National NORML press list.

Seasonal Work — KYCannaCon Production (September–March)

KYCannaCon is KYNORML's single largest revenue moment and its most visible community asset. From September through March, conference production runs alongside (not instead of) the monthly rhythm. See KYCannaCon Conference Playbook for the full detail — this is the monthly milestone view.

| Month | Production Milestone |
| --- | --- |
| June–August | Sponsor outreach begins — Presenting Sponsor ($8,500) and Session Sponsors ($3,000) are the priority; venue call to Louisville Tourism CVB for proposals |
| September | Venue contract signed; speaker invitations sent; save-the-date teaser content starts on social |
| October | Speaker lineup in progress (confirmed and tracking); AV/tech vendor locked; sponsor pipeline active |
| November | Save-the-date press release issued — first official public announcement; early bird ticket sales open; email to full 8,000-person list |
| December | Year-in-review press release; sponsor follow-ups; speaker confirmations; full agenda draft in progress |
| January | Legislative session preview press release (runs when GA convenes); early bird ticket deadline; Session Sponsor final asks |
| February | Speaker lineup press release (early Feb); Presenting Sponsor reveal (mid-Feb — consider Kentucky Lantern embargo); final ticket push; exhibitor spots fill |
| March | Final countdown press release; event day; event recap press release day-of or day-after; session wrap-up release post-GA adjournment |
| April | Convert event attendees to members; post-event sponsorship debrief; capture proof points (attendance, quotes, photos) for next year's sponsor pitch |

Conference format: one-day, conference-format (not expo). Three content tracks: Policy, Industry, Patient/Community. Legislator panel is the centerpiece. No table-only sponsorships — every sponsor buys access to the content/audience. Capacity target: 175–200. Do not return to KICC (too large — reads as empty with 150–200 people).

Annual Work

These don't happen every month but they define the chapter's long-term health. The compliance calendar check (last week of every month) is what prevents any of these from becoming surprises.

January — Start of fiscal year

☐  Board approves annual operating budget — income and expense targets by category

☐  Board conflict-of-interest policy signed by all members at first meeting

☐  Review and update the annual operating budget template in Financial Box

May 15 — 990 Filing Deadline

☐  File Form 990 with the IRS — 990-N if gross receipts under $50K, 990-EZ if $50K–$200K, full 990 if over $200K

☐  Begin prep 60 days early (mid-March) — don't start the week it's due

☐  Confirm CGN files its own separate 990 — these are two separate entities

Incorporation Anniversary — State Annual Report

☐  File the Kentucky state annual report with the Secretary of State

☐  Confirm the exact due date from the original incorporation filing record — it's the anniversary, not a calendar date

Annual — Charitable Solicitation Registration

☐  Confirm Kentucky charitable solicitation registration is current

☐  Required before any active fundraising — renew before it lapses, not after

Annual — Board Governance

☐  Board elections / officer term renewals per the bylaws schedule

☐  Confirm no seats have been vacant more than 60 days

☐  Update board roster in the Handoff Notes below

Annual — Strategic Review

☐  Conduct the annual chapter review using the scorecard and questions in Chapter Health Dashboard

☐  Answer the five annual review questions as a board: biggest win, biggest failure, revenue sustainability, right people in right roles, one thing that would make the biggest difference next year

Annual — Merch

☐  Review current product line — what's selling, what's not

☐  Decide on any new product for the year; brief the designer; update the Canva brand kit if needed

☐  Confirm the Zeffy or fulfillment setup for merch sales is current

Annual — Google Ad Grants Review (via CGN)

☐  Confirm the $10,000/month in free Google advertising via CGN is being actively managed — currently noted as idle in vault records

☐  If idle: either activate it (requires a landing page strategy and keyword targeting) or document why it's being left unused

Handoff Notes — What a New Person Needs to Know That Isn't Written Anywhere Else

(Fill this in before the transition is complete. Write the actual answer next to each item — not just a checkmark. A checked box with no information is not a handoff.)

Access and credentials

☐  Books (Wave or QuickBooks) — login owner: ___________ / who else has access: ___________

☐  Action Network — admin login owner: ___________ / list size at transition date: ___________

☐  Zeffy — admin login owner: ___________ / (c)(4) verification confirmed: Y / N

☐  Monday.com — board owner / billing contact: ___________

☐  Buffer / Meta Business Suite — admin owner: ___________

☐  Google Workspace — admin owner: ___________ / relationship to CGN Workspace: ___________

☐  Canva — brand kit owner: ___________

☐  Website / CMS — host: ___________ / domain registrar: ___________ / CMS login owner: ___________

☐  Social accounts (FB, IG, Threads) — transferred as full owner, not shared login: Y / N

☐  Bank — bank name: ___________ / account type(s): ___________ / authorized signatories: ___________ / process to add/remove signatory: ___________

People

☐  Full board roster: name / role / term start-end / renewal date / email / phone — for every seat

☐  Shealonda: role ___________ / responsibilities ___________ / staff or contractor ___________ / how to reach ___________

☐  Maurice: role ___________ / responsibilities ___________ / staff or contractor ___________ / how to reach ___________

☐  James: role ___________ / responsibilities ___________ / staff or contractor ___________ / how to reach ___________

☐  Key external relationships who need a personal heads-up about the transition (not a mass announcement): ___________

Money and commitments in motion

☐  Actual cash on hand and reserve balance at transition date (confirmed from books): ___________

☐  Any informal agreements, verbal commitments, or in-progress conversations not yet logged in Monday.com: ___________

☐  Outstanding invoices, pending reimbursements, or unpaid bills: ___________

☐  KYCannaCon production status — what's confirmed vs. still in conversation: ___________

☐  Any active grant applications (via CGN or otherwise): ___________

Compliance

☐  Date of last 990 filing and next due date confirmed: ___________

☐  State annual report — incorporation anniversary date: ___________ / last filed: ___________

☐  Charitable solicitation registration — current status and renewal date: ___________

☐  Date of last board meeting with minutes on file: ___________

First 30 Days — A Ramp for Whoever Steps Into This Role

Week 1 — Get access, not action. Work through the Systems & Access Map. Confirm you can log into every platform as an admin. Don't change anything yet — just confirm access. Meet with the outgoing Deputy Director and walk through the Handoff Notes together, live, while they can still answer follow-up questions in real time.

Week 2 — Read before you run. Read Marketing Master Calendar, Revenue Action Dashboard, and Weekly Action Plan in full. Pull the most recent monthly financial snapshot and KPI numbers — even if you didn't generate them, knowing where the chapter stood the month before you arrived is your starting line.

Week 3 — Shadow the rhythm. If there's a board meeting, sponsor call, batch session, or scheduled email send in this window, sit in on it — ideally with the outgoing person present to provide context on the why, not just the what.

Week 4 — Run one cycle with a safety net. Execute the monthly rhythm yourself, with the outgoing person available to answer questions but not doing the work for you. By the end of this week, you should be able to run the next full month solo.

The test that tells you the handoff is complete: can you run a full monthly cycle — financial snapshot, KPI pull, fundraising touches, board prep, compliance check, marketing sync — without asking the outgoing Deputy Director a single question? If yes, the transfer is done. If no, that's not failure — it's a signal of exactly what still needs to be documented.

Glossary — Shorthand You'll See Everywhere in This Vault

| Term | What It Means |
| --- | --- |
| KYNORML | Kentucky NORML — the 501(c)(4) chapter this document covers |
| CGN | Common Good Network — the affiliated 501(c)(3) education arm (separate legal entity) |
| VMP | Verdant Management Partners — Lauren Bratcher's professional services company; produces KYCannaCon and consults for other chapters |
| VV | Verdant Ventures LLC — Lauren's personal vendor entity; bills VMP for her work |
| GA session | The Kentucky General Assembly's annual legislative session (roughly January–March/April) — the single biggest advocacy and press driver each year |
| KYCannaCon | KYNORML's signature annual cannabis policy conference, timed to the GA session; Year 4 is the first since Kentucky dispensaries opened |
| The 8k list | Shorthand for the ~8,000-person Action Network email list — KYNORML's largest single audience asset |
| The Chapter Box | The replicable operations package (governance, finance, brand, health dashboard, etc.) VMP packages and sells to other NORML state chapters |
| VMP chapter outreach | VMP's consulting revenue stream — selling the Chapter Box to other chapters; takes 30–45 days to start converting after outreach begins |
| Batch session | The 2.5-hour bi-weekly social media content creation and scheduling block per Track 2 - Social Media System — the only time social content is created, except for reactive posts |

Related Files

- Financial Box — bookkeeping setup, budget template, financial controls, vendor contracts

- Governance Box — board structure, bylaws, IRS compliance, banking, minutes template

- Chapter Health Dashboard — full KPI tracker, health indicators, quarterly/annual review

- Marketing Master Calendar — 12-month marketing and revenue view

- Track 1 - Email Campaign System — all email campaign templates

- Track 2 - Social Media System — batch workflow, pillar rotation, platform formats

- Track 4 - PR Response System — reactive and planned press workflows and templates

- KYCannaCon Conference Playbook — full conference production system

- Zeffy Membership Setup Guide — step-by-step membership tier setup

- Revenue Action Dashboard — current revenue sprint and scorecard

- Weekly Action Plan — week-by-week execution detail

- ! NORML Chapter Box — full index of all chapter operating system components