Common Good Network Gaming Lounge Business Plan

Bowling Green, Kentucky | Draft prepared for lease approval, application approval, and internal strategy | June 30, 2026

Decision recommendation: approve lease pursuit if management verifies insurance requirements, operating authority, opening staffing coverage, and pre-opening cash controls before signing. The current $25,000 request covers lease-readiness cash, while Arrow's post-opening grant and equipment/service support materially reduce launch risk.

# 1. Executive Summary

Common Good Network proposes to open a gaming lounge in Bowling Green, Kentucky as a structured, community-centered recreation venue offering console/PC gaming, tournaments, memberships, private events, and partner programming. The launch footprint includes 35 gaming machines and an initial schedule of 6 days per week, 8 hours per day. The concept should be positioned as a safe, supervised, social gaming environment rather than a passive arcade.

[ASSUMPTION: Common Good Network will operate the lounge as a mission-aligned community enterprise with earned revenue, not as a gambling venue, adult-only bar, or purely charitable drop-in space.]

The immediate funding requirement is $25,000: $10,000 for the opening cash till, $8,000 for first and last month rent, $2,000 for utility deposits, and $5,000 for an operating buffer. Monthly rent is confirmed at $4,000 and includes triple net and CAM. Arrow will grant $25,000-$35,000 once the doors are open and owns all gaming-related equipment and service machines. [GAP: Insurance structure, furniture/buildout items outside gaming equipment, licensing, opening inventory, and pre-opening payroll funding still need confirmation.]

The local case is credible but not automatic. Bowling Green's growing population and WKU's student base support demand for affordable social recreation, but existing family entertainment centers, youth/community centers, and adult gaming venues already serve parts of the market. Common Good Network's defensible lane is supervised, community-first gaming with consistent programming, memberships, and partner access.

The Year 1 projection shows $219,782 in revenue and $53,717 in operating surplus before taxes, debt service, depreciation, owner distributions, and Arrow grant proceeds. With the Arrow grant, first-year cash resilience improves materially after opening. The weakest assumption remains paid traffic: the base case requires 32 paid drop-in visits per open day plus 80 average monthly members in Year 1, equal to less than one paid drop-in visit per machine per open day.

[GAP: Existing financials, confirmed opening date/deadline, exact location, square footage, staffing plan, insurance quotes, legal entity details, and written Arrow grant/equipment terms were not provided.]

# 2. Company Description

Common Good Network's Gaming Lounge will be a community-oriented gaming and events venue in Bowling Green, KY. The launch plan starts with 35 gaming machines and an operating schedule of 6 days per week, 8 hours per day. The business will monetize through hourly/day-pass gaming access, memberships, tournaments, private events, partner rentals, light concessions, merchandise, and potential sponsorships.

The concept fits best as a hybrid between entertainment venue and community program platform. That hybrid structure matters for lease and internal approval: the lounge must generate enough recurring revenue to cover rent and labor, while also creating mission value through supervised recreation, skill-building events, and partner access.

## Mission Fit

Provide a safe, supervised place for social gaming and positive peer connection.

Create low-cost entertainment access for students, families, and young adults.

Use tournaments, leagues, and workshops to build teamwork, digital confidence, and community belonging.

Build a flexible venue that can host partner nights, youth groups, school-adjacent programs, and community events.

## Business Model

| Revenue stream | Operating logic | Year 1 role |
| --- | --- | --- |
| Drop-in gaming | Hourly/day-pass access to consoles, PCs, racing/sports games, fighting games, and party games. | Primary traffic driver |
| Memberships | Monthly recurring access, discounted tournaments, member-only nights, and guest passes. | Stabilizes cash flow |
| Tournaments/events | Smash, sports titles, racing nights, school break events, birthday packages, and team competitions. | High-margin programmed revenue |
| Private rentals | Reserved blocks for youth groups, partners, birthdays, and team-building. | Predictable off-peak monetization |
| Concessions/merch | Snacks, drinks, small branded goods, and tournament merchandise. | Margin support, not core thesis |
| Sponsorships | Local business sponsorship of tournaments, stations, scholarships, or leagues. | Upside not relied on in base case |

# 3. Market Analysis

## Local Demand Context

Bowling Green is Kentucky's third-largest city by 2020 Census count and remains a growing regional market. U.S. Census QuickFacts estimated Bowling Green city population at 78,505 in 2025, up 8.6% from the 2020 estimate base. WKU reported preliminary fall 2025 enrollment of 15,920 students, creating a visible student and young-adult demand base for affordable, social entertainment.

Commercial rent context supports the confirmed rent. CommercialCafe reported Bowling Green commercial real estate asking rents averaging $19.26 per square foot, with listed range examples from $11 to $27.50 per square foot. Rent is confirmed at $4,000 per month including triple net and CAM. [ASSUMPTION: If the lounge occupies approximately 2,000 square feet, total rent equals about $24 per square foot annually, which is within the observed listed market range but toward the higher end.]

## Competitive Landscape

| Category | Examples / evidence | Implication for Common Good Network |
| --- | --- | --- |
| Family entertainment | Ralphie's Fun Center advertises 40+ arcade games and attractions; Southern Lanes promotes bowling, laser tag, billiards, batting cages, arcade games, and party rooms. | Compete on community programming, gaming specialization, and recurring memberships rather than broad attractions. |
| Youth/community centers | Boys & Girls Club of Bowling Green's Teen Center serves ages 13-18 and offers multiple gaming systems, laptops, pool table, seating, and programming. City recreation centers offer game rooms and youth programs. | Partner, do not duplicate. Common Good should serve evenings, tournaments, families, young adults, and partner events. |
| Adult gaming/entertainment | The Mint Gaming Hall promotes nearly 500 gaming machines, sportsbook, Top Golf Swing Suites, food, bar, and live entertainment. | Differentiate clearly from gambling and adult gaming. The lounge should be safe, supervised, and mission-aligned. |
| Regional esports/barcade options | Search results and local discussion indicate stronger barcade/esports options in larger nearby markets such as Nashville, Louisville, Lexington, or Elizabethtown. | Opportunity exists for a local, non-bar, accessible gaming hub if programming is consistent. |

## Target Customers

Students and young adults seeking affordable evening/weekend social gaming.

Parents and families seeking supervised recreation, parties, and school-break activities.

Competitive and casual gamers who want tournaments, leagues, and reliable equipment.

Community partners needing a flexible, youth-friendly event space.

Local businesses that want sponsorship visibility with youth, family, and college-age audiences.

## Market Position

Common Good Network should position the lounge as Bowling Green's community gaming hub: structured, safe, local, affordable, and programmable. The plan should avoid claiming there is no competition. The defensible claim is that no identified local competitor combines mission alignment, supervised social gaming, tournament programming, memberships, and partner-use flexibility in one venue.

# 4. Organization & Management

[GAP: Legal entity, ownership/governance structure, board composition, manager name, and operating authority have not been provided.] For this draft, the plan assumes Common Good Network will designate one accountable operating lead with authority over scheduling, staffing, cash controls, vendor relationships, safety procedures, and partner programming.

## Recommended Management Structure

| Role | Core responsibilities | Approval relevance |
| --- | --- | --- |
| Board / sponsor group | Approve lease, budget, cash policy, insurance, risk controls, and monthly performance review. | Shows oversight and protects mission/financial discipline. |
| Operating manager | Daily operations, staffing, events calendar, memberships, POS reconciliation, customer standards. | Single accountable operator is essential for lease confidence. |
| Program/event coordinator | Tournaments, partner nights, youth-friendly programming, school-break events. | Turns the venue into a programmed business, not idle space. |
| Part-time attendants | Check-in, station reset, concessions, safety monitoring, basic troubleshooting. | Controls customer experience and equipment care. |
| Bookkeeper/accountant | Monthly financials, sales tax tracking, payroll support, bank reconciliation. | Required for internal strategy and lease credibility. |

## Controls Required Before Opening

Written cash-handling policy for the $10,000 opening cash till, including maximum drawer levels, deposit timing, and dual-control reconciliation.

POS system that separates drop-in sales, memberships, events, concessions, discounts, and refunds.

Insurance binder covering general liability, property/equipment, workers' compensation if applicable, and events.

Rules of conduct, youth check-in/check-out policy, incident reporting process, and equipment damage policy.

Monthly board/internal dashboard: revenue by stream, paid visits, memberships, event count, gross margin, cash balance, incidents, and repairs.

# 5. Products and Services

| Offering | Pricing assumption | Operating notes |
| --- | --- | --- |
| Drop-in gaming pass | $14 average ticket across hourly/day-pass mix | Base model assumes 32 paid drop-in visits per open day in Year 1. |
| Monthly membership | $29/month average realized membership price | Includes recurring access benefits and discounts; Year 1 assumes 80 average members. |
| Tournament entry | $10-$20 per person or included in event packages | Use weekly/biweekly cadence; prizes should be capped and sponsored when possible. |
| Birthday/private event package | $200-$350 depending on duration and group size | Base model averages event revenue at $250 per event in Year 1. |
| Partner rental block | $150 average rental block | Discounted partner use can be mission-aligned, but free use must be budgeted. |
| Concessions | $6 average concession spend by 35% of paid visitors | Keep menu simple: packaged snacks, bottled drinks, low-waste inventory. |

The core service standard should be reliable access, clean equipment, clear scheduling, and consistent programming. Gaming lounges fail when the room becomes idle equipment. Revenue depends on a visible calendar and repeatable reasons to return.

# 6. Marketing and Sales Strategy

## Launch Priorities

Secure founding member commitments before lease signing. Target 100 paid or pledged founding memberships before opening.

Build a 90-day opening calendar before opening day, including weekly tournament nights, family blocks, student nights, and partner events.

Use local ambassadors: WKU students, school-adjacent groups, youth leaders, gamers, and parent advocates.

Sell event packages before opening to validate demand and generate deposits.

Create sponsorship packages for station naming, tournament sponsorship, youth access scholarships, and league nights.

## Sales Targets

| Metric | Pre-opening target | First 90-day target | Reason |
| --- | --- | --- | --- |
| Founding memberships | 100 pledged / 60 paid | 80 active average | Validates recurring demand and lowers cash risk. |
| Private events booked | 8 deposits | 18 events completed | Creates opening cash and word-of-mouth. |
| Partner/rental nights | 6 commitments | 12 completed | Uses off-peak hours and supports mission fit. |
| Email/SMS list | 1,000 contacts | 1,500 contacts | Reduces dependence on paid ads. |
| Sponsor commitments | $2,500 pledged | $5,000 annualized pipeline | Offsets prizes, access scholarships, and launch marketing. |

## Marketing Channels

Short-form social content showing tournaments, station setup, winners, birthday events, and community nights.

Direct outreach to schools, churches, youth-serving nonprofits, apartment communities, employers, and WKU student groups.

Launch-week offers that convert to memberships rather than one-time discounts.

Local sponsorships and co-hosted events with partners who already reach the target audience.

Referral rewards for members and party hosts.

# 7. Funding Request

The immediate funding request is $25,000. This request is structured for lease readiness and opening liquidity. Arrow's commitment to grant $25,000-$35,000 after opening and to own/service all gaming-related equipment materially reduces the unfunded equipment risk. It does not remove the need to confirm insurance, non-gaming buildout/furniture, inventory, staffing, and written Arrow terms.

| Use of funds | Amount | Purpose / control |
| --- | --- | --- |
| Opening cash till | $10,000 | Start-up cash liquidity, change bank, and controlled operating cash. Requires written cash policy. |
| First and last month rent | $8,000 | Assumes $4,000/month rent. Supports lease execution. |
| Utility deposits | $2,000 | Deposits for electric, internet, water, waste, and related services. |
| Operating buffer | $5,000 | Short-term cushion for early timing gaps, repairs, supplies, and launch variance. |
| Immediate lease-readiness total | $25,000 | Minimum cash requirement before opening. |
| Arrow post-opening grant | $25,000-$35,000 | Supplemental source expected after doors open; should not be spent or pledged before written terms and timing are confirmed. |

[GAP: Written Arrow terms, insurance requirements, furniture, signage, buildout outside gaming equipment, permits, legal/accounting setup, POS hardware, opening inventory, and pre-opening payroll still need confirmation.] If these items are not already secured or covered by Arrow/partners, the true funding need is higher than the initial $25,000 lease-readiness request.

# 8. Financial Projections

## Key Modeling Assumptions

| Assumption | Year 1 base case | Why it matters |
| --- | --- | --- |
| Operating days | 312 days/year, 6 days/week | Sets traffic capacity and staffing requirement. |
| Operating hours | 8 hours/day at startup | Supports controlled staffing, equipment monitoring, and demand testing before expanding hours. |
| Gaming machines | 35 machines | Capacity supports the base traffic model; utilization can be measured by paid visits per machine. |
| Paid drop-in visits | 32 visits/open day | Weakest assumption; drives core revenue. |
| Average drop-in ticket | $14.00 | Blended hourly/day-pass realized price after discounts. |
| Average members | 80 active monthly members | Stabilizes recurring revenue. |
| Membership price | $29/month | Affordable positioning with recurring cash flow. |
| Events | 8/month at $250 average | Requires a programmed calendar and sales outreach. |
| Rent | $4,000/month including NNN/CAM | Confirmed by user; may change only if insurance arrangement changes. |
| Square footage | 2,000 SF | Assumed for rent reasonableness; must be confirmed. |
| Gaming equipment/service | 35 machines owned and serviced by Arrow | Reduces capital expenditure and maintenance risk. |
| Arrow grant | $25,000-$35,000 after opening | Improves runway after doors open; timing and written terms still need confirmation. |

## Revenue Projection

| Revenue stream | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Drop-in gaming | $139,776 | $180,960 | $224,640 |
| Memberships | $27,840 | $40,020 | $52,200 |
| Events / tournaments / parties | $24,000 | $33,000 | $43,200 |
| Concessions / merch | $20,966 | $31,387 | $40,435 |
| Partner rentals / program blocks | $7,200 | $10,800 | $14,400 |
| Total revenue | $219,782 | $296,167 | $374,875 |

## Operating Expense Projection

| Expense category | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Concession/merch cost of goods | $7,338 | $10,985 | $14,152 |
| Payment processing / platform fees | $6,593 | $8,885 | $11,246 |
| Labor and payroll taxes | $68,000 | $82,000 | $98,000 |
| Rent incl. NNN/CAM | $48,000 | $49,440 | $50,923 |
| Utilities | $12,000 | $13,000 | $14,000 |
| Internet / network services | $3,600 | $3,900 | $4,200 |
| Insurance | $5,000 | $5,500 | $6,000 |
| Maintenance / equipment reserve | $7,200 | $9,000 | $12,000 |
| Marketing | $7,500 | $9,000 | $11,000 |
| Supplies/security | $5,400 | $6,200 | $7,000 |
| Software / licenses / POS | $4,200 | $4,800 | $5,400 |
| Admin / accounting / professional | $4,800 | $5,400 | $6,000 |
| Miscellaneous / contingency | $6,434 | $7,300 | $8,100 |
| Total operating expenses | $166,065 | $215,410 | $248,021 |
| Operating surplus (pre-tax/debt/depr.) | $53,717 | $80,757 | $126,854 |

## Year 1 Cash Flow View

| Cash flow item | Amount | Notes |
| --- | --- | --- |
| Starting lease-readiness funds | $25,000 | Provided funding requirement. |
| First/last rent and utility deposits | ($10,000) | Lease cash out before/at opening. |
| Opening cash till | ($10,000) | Restricted operating cash/change bank; not treated as spend if retained. |
| Operating buffer retained | $5,000 | Available cushion after deposits/till allocation. |
| Year 1 operating surplus | $53,717 | Before taxes, debt service, depreciation, and owner distributions. |
| Estimated end-of-year operating cash before distributions | $58,717 | Assumes no debt service and no unbudgeted buildout/equipment purchases. |
| Arrow grant proceeds after opening | $25,000-$35,000 | Not included in operating surplus; improves cash runway when received. |
| Estimated end-of-year cash including Arrow grant | $83,717-$93,717 | Assumes written grant terms are satisfied and funds are received in Year 1. |

[GAP: Tax status, depreciation, debt service, payroll structure, and owner/manager compensation policy were not provided. The projection should not be used for tax or lending approval without those details.]

## Break-Even View

| Break-even metric | Base-case estimate |
| --- | --- |
| Estimated annual fixed operating costs | $153,534 |
| Estimated variable cost rate | 13.5% of revenue |
| Contribution margin | 86.5% |
| Annual break-even revenue | $177,496 |
| Monthly break-even revenue | $14,791 |
| Required drop-in equivalent at $14 ticket | 35 visits/day if relying only on drop-ins |
| Base-case Year 1 revenue | $219,782 |
| Year 1 margin above break-even | $42,286 |

The base case clears break-even, and Arrow's post-opening grant materially improves cash runway after launch. The remaining risk is timing: if paid traffic is weak before the grant arrives, or if insurance/buildout costs are higher than expected, the lounge may still need additional short-term working capital. The board should require a 90-day pre-opening sales plan and weekly launch dashboard.

## Sensitivity Check

| Scenario | Revenue impact | Likely result |
| --- | --- | --- |
| Base case | $219,782 Year 1 revenue | $53,717 operating surplus before taxes/debt/depreciation. |
| Traffic 20% below plan | Approx. $191,827 revenue | Surplus falls materially; cash cushion becomes thin but may remain positive if labor flexes. |
| Traffic 30% below plan | Approx. $177,860 revenue | Near break-even; additional working capital likely needed. |
| Events underperform by 50% | Revenue down $12,000 | Still viable if drop-in and membership targets hold. |
| Rent 10% higher | Expense up $4,800/year | Manageable only if traffic and membership targets hold. |

# 9. Appendix

## Missing Critical Inputs

[GAP: Existing financials or confirmation that none exist.]

[GAP: Deadline for final version and any lease/application submission requirements.]

[GAP: Exact address, square footage, lease term, escalation, security deposit, tenant improvement responsibilities, insurance obligations, and permitted use clause.]

[GAP: Written Arrow grant terms, gaming equipment inventory, gaming station count, service standards, replacement plan, furniture list, POS/security/network setup, and what items fall outside Arrow's responsibility.]

[GAP: Legal entity, tax status, bank account controls, board authorization process, insurance quotes, licenses/permits, and payroll approach.]

[GAP: Staffing names, compensation commitments, volunteer policy if used, youth safety policy, and background-check requirements where applicable.]

## First 30 Approval Conditions

Confirm full lease economics in writing: rent, term, escalations, deposits, utilities, CAM, insurance requirements, signage, buildout responsibilities, and early termination exposure.

Document all opening assets already secured and identify any unfunded equipment/buildout needs before signing.

Approve a cash control policy for the $10,000 till and define who can access, reconcile, and deposit funds.

Obtain insurance quotes and confirm allowed use with landlord and insurer.

Pre-sell founding memberships, private events, and partner nights to reduce launch-risk guesswork.

Build a 13-week opening cash forecast using actual lease and staffing numbers.

## Sources Reviewed

U.S. Census Bureau QuickFacts, Bowling Green city, Kentucky: https://www.census.gov/quickfacts/fact/table/bowlinggreencitykentucky/PST045224

WKU News, fall enrollment and retention update: https://www.wku.edu/news/articles/index.php?articleid=12797&view=article

CommercialCafe, Bowling Green commercial real estate rent context: https://www.commercialcafe.com/commercial-real-estate/us/ky/bowling-green/

Ralphie's Fun Center arcade page: https://ralphiesfuncenter.com/services/arcade/

Southern Lanes Family Fun Center: https://www.southernlanesinc.com/

Boys & Girls Club of Bowling Green Teen Center: https://www.bgcbg.org/teen-center/

Bowling Green Parks and Recreation athletics/community programming: https://www.bgky.org/bgpr/athletics

The Mint Gaming Hall Bowling Green: https://themintbowlinggreen.com/

Research note: external sources were used only for local market context, competitor positioning, and rent reasonableness. All projections are assumption-driven because operating history and confirmed lease/equipment details were not provided.